## APQP Status Report
Quality Assurance Agreement with Production Material Suppliers
APQP Status Report
Revisions no. |  |  | Date (YYYY-MM-DD) |  |  |  | Status samples
Customer |  |  | Supplier |  |  |  | Customer input
Name |  |  | Name |  |  |  | Initial sampling date
Customer site |  |  | Production site |  |  |  | PPAP submission level
Drawing no. |  |  | Drawing no. |  |  |  | Project class
Revision level |  |  | Revision level
Description |  |  | Description
Customer Data |  | Responsible | Phone |  | Supplier data |  | Responsible |  | Phone
Project management |  |  |  |  | Project management
Development |  |  |  |  | Development
Design |  |  |  |  | Design
Production |  |  |  |  | Production
Quality |  |  |  |  | Quality
Purchasing |  |  |  |  | Sales
Packaging technology
Overview prototypes |  |  | Confirmed due date (YYYY-MM-DD) |  |  | Quantity | Status % | Comment
Mass production ramp-up |  |  | Date (YYYY-MM-DD) |  |  | Quantity
APQP Elements |  |  | Status | Target date (YYYY-MM-DD) |  | Actual date (YYYY-MM-DD) | Responsible | Comments (further comments in action plan)
1 | Customer order
2.1 | Customer specifications
2.2 | Contract review
3 | Craftsmanship - appearance
4 | Design FMEA
5 | Design review
6 | Design verification plan - DVP
7 | Quality planning for subcontractor
8.1 | Equipment and tools
8.2 | Inspection methods and inspection equipment
9 | Inspection plan / control plan for prototype parts
10 | Production and inspection of prototype parts
11 | Design freeze (drawings / specifications)
12 | Manufacturing feasibility confirmation
13 | Process flow chart and mass production layout
14 | Process FMEA
15 | Inspection equipment capability
16 | Pre-production / pre-launch inspection plan
17 | Process Instructions
18.1 | Logistics concept
18.2 | Packaging materials
19 | Production trial run
20 | Mass production inspection plan / control plan
21 | Preliminary process capability study
22 | Technical tests on mass production parts - PVP
23 | Initial sampling
Note on D34: - green (G): The current status of the function and quality aims corresponds with the planned date. The achievement of the function and quality aims that have been specified for the current phase is not endangered. The completion of the element must be documented by filling in the actual date. - yellow (Y): Date/Quality of the element are endangered; appropriate actions and responsible persons should already be defined. Start of mass production is not endangered. - red (R): Date/Quality of the element have not been fulfilled. Start of mass production (elements 22 and 23) is endangered. If an element which has been classified yellow/red has been successfully closed (even after the target date) and the late closing/correction does not have a negative effect on the date/quality of the project/elements, or the relevant compensatory measures have been taken, the element can be re-classified green.
Note on G34: Option of linking with MS-Project In this instance the dates in MS-Project have to be linked manually and once only to the respective APQP elements (highight MS-Project date -> APQP checklist: highlight "Actual date" cell -> EDIT -> Insert contents -> Link and select Format EXCEL 8.0). In the event of further changes, the dates in the checklist will be updated automatically.
Note on B35: Customer Order (APQP Element 1) Aim: Formal placing of an order by the customer so that investments can be effected on schedule by the supplier. Expectations: The customer selects a supplier and informs the supplier of the decision Documentation with supplier: • Nomination Letter • Individual order indicating project classification for advanced product quality planning (APQP) and submission level for sampling • Delivery schedule Submission to customer: Status in APQP Status Report
Note on E35: Order phase Target date: For order allocation
Note on B36: Customer Specifications (APQP Element 2.1) Customer specifications include, for example, the design briefs, drawings or specifications which are required at the start of a project. Aim: To avoid misunderstandings by using clear specifications. Expectations: The supplier must be familiar with the requirements of the product / project, e.g. • installation situation • ambient conditions • functional performance requirements • dimensions • weight • material • reliability (life) • guarantee objectives • quality objectives for incoming parts (ppm rating, defect levels and rejection quotas) • capacity data or volumes • milestones - checking the program status - final definition of the design (Design Freeze) - prototype parts - pre-production - initial volume production samples Documentation with supplier: • Design briefs, drawings or specifications • List showing issue level of the individual documents Submission to customer: • Status in APQP Status Report • List showing issue level of the individual documents
Note on E36: Quotation/Order phase Target date: Prior to submission of quotation
Note on B37: Contract Review (APQP Element 2.2) Aim: To carry out a commercial and technical assessment of the documents provided by the customer to check that they are complete, up-to-date and feasible. Expectations: Before entering into a delivery agreement with the customer a contract review is carried out to ensure that: • the product requirements have been suitably defined and documented (e.g. drawing, specification, design requirements) • (deviating requirements are clarified prior to submitting the quotation or closing the contract (e.g. drawing deviations, drawing modifications made by the customer, delivery dates, price) • the defined requirements can be met. The quotation is prepared following a pan-divisional production feasibility analysis Documentation with supplier: • Confirmation of capacity • Confirmation of manufacturing feasibility Submission to customer: • Status in APQP Status Report • Confirmation of production feasibility, e.g. to QSV / S 296001 Part 1 - Appendix 4 • Confirmation of capacity to QSV / S 296001 Part 1, Appendix 5
Note on E37: Target date in accordance with enquiry text Prior to order allocation
Note on B38: Craftsmanship (appearance) (APQP Element 3) Aim: To define characteristics relating to appearance, texture, handling ability and acoustics. Expectations: • The supplier should be familiar with and meet the requirements that relate to the above-mentioned characteristics • In order that the characteristics can be checked, features catalogues and reference samples etc. should be made available and agreed with the customer Documentation: Features catalogues and reference samples Submission to customer: Status in APQP Status Report
Note on E38: Quotation/Order phase Target date: Prior to submission of quotation
Note on B39: Design-FMEA (APQP Element 4) Only applicable to suppliers with personal responsibility for product development. A Design-FMEA is a systematic procedure used to ensure that potential development and design defects and their respective causes have been taken into account and have been countered by preventive measures within a technical pan-divisional team. The Design-FMEA must cover all functions of the product and must take into account experiences and concerns. Aim: To prevent defects during product development. Expectations: • Problems relating to product layout are solved in good time so that all sampling and volume production dates can be observed • Checks can be made on progress in respect of the Design Verification Plan • Unforeseen potential defect modes which occur at the design review stage must be incorporated into the Design-FMEA and the layout criteria modified in agreement with the customer • Checks must be made on potential improvements as regards product reliability and manufacturing costs • Checks must be made on progress in terms of achieving goals relating to reliability, quality, costs and planning • Influencing defect modes are described and assessed and, where necessary, corrective measures are introduced and monitored by the persons responsible Documentation with supplier: Design-FMEA Submission to customer: • Status in APQP Status Report • Cover sheet to Design-FMEA including participants and issue level
Note on E39: Target date: Final date for initial preparation of FMEA Start: Prior to DVP start date - from INA design release Finish: Completion of outstanding FMEA points upon introduction of initial samples
Note on B40: Design Review (APQP Element 5) Aim: To prevent misunderstandings and problems; to monitor the progress of measures and to ensure that objectives are met. Expectations: • Problems relating to product layout are solved in good time so that all sampling and volume production dates can be observed • Checks can be made on progress in respect of the Design Verification Plan • Unforeseen potential defect modes which occur at the design review stage must be incorporated into the Design FMEA and the layout criteria modified in agreement with the customer • Checks on potential improvements as regards product reliability and manufacturing costs • Checks must be made on progress in terms of achieving goals relating to reliability, quality, costs and planning Documentation with supplier: Meeting reports prepared by the supplier or the customer Submission to customer: Status in APQP Status Report
Note on E40: Target date: Prior to order allocation
Note on B41: Design Verification Plan - DVP (APQP Element 6) Only applicable to suppliers with personal responsibility for product development. Aim: Systematic planning of all tests or calculations to check whether the product or design is suitable for the application. Expectations: • The suitability of the product must be proven by means of planned tests or calculations • Responsibility for tests on volume products must be defined (see APQP element 22) Documentation with the supplier: • Design Verification Plan • Test reports, layout calculations and tolerance studies Submission to customer: • Status in APQP Status Report • Status for design verification (current status of DVP)
Note on E41: Target date: Completion of initial DVP Start: The preliminary DVP should already have been prepared during the quotation phase (costs) on the basis of the System FMEA Product. This is continued once definite product development work is underway. Finish/Completion of calculations/tests: For presenting of initial samples
Note on B42: Quality Planning for Subcontractor (APQP Element 7) The suppliers must forward the APQP requirements to their subcontractors, check implementation and give the results in summarized form in the APQP Status Report. Aim: To provide a clear illustration of the progress that a subcontractor is making on a project for process/products associated with increased risks, or at the customer's specific request. Expectations: • The supplier must carry out a risk assessment and specify the extent of his subcontractors' participation in the advance quality planning process • The suppliers must check the progress of the project on a regular basis with their subcontractors, particularly if they deliver these products with "special features“ Documentation with supplier: Subcontractor’s status report on the progress of the project Submission to customer: • Status in APQP Status Report • Detailed schedules at the customer’s request
Note on E42: Target date: Initial sampling of the purchased parts must be completed before the date of initial sampling for the customer (continuous monitoring)
Note on B43: Equipment and Tools (APQP Element 8.1) Aim: Capable / released operating materials Expectations: • Planning (monitoring of dates) and provision of all necessary operating materials • Deadlines for the procurement or manufacture of equipment and tooling must be monitored • The equipment and tooling should be tested prior to the production trial run Documentation with supplier: Schedules, capacity plans, proof of capability established within the framework of the initial sampling process Submission to customer: • Status in APQP Status Report • Detailed schedules at the customer’s request
Note on E43: Target date: Final date for the last co-ordinated and released operating materials prior to production trial run/initial sample production
Note on B44: Inspection Methods and Inspection Equipment (APQP Element 8.2) Aim: To obtain inspection methods which have been coordinated with the customer and inspection equipment which is suitable for the measuring task. Expectations: • The inspection methods should be coordinated between the supplier and the customer • Deadlines for the procurement or manufacture of equipment and tooling must be monitored • Proof of inspection equipment capability and, where necessary, inspection process suitability must be provided Documentation with supplier: • Stipulation in control plan, proof of capability within the framework of the initial sampling process Submission to customer: • Status in APQP Status Report
Note on E44: Target date: Agreed inspection methods documented in control plan (production) Final date for agreed and released inspection equipment prior to production trial run/initial sample production. Start: When inspection features are defined Finish: Prior to ordering inspection equipment
Note on B45: Inspection Plan / Control Plan for Prototype Parts (APQP Element 9) Aim: To secure the prototype quality. Expectations: • The type and scope of the inspections and the corresponding inspection equipment for prototypes are defined and agreed with the customer • All "special features“ are included Documentation with supplier: Control plan for prototypes Submission to customer: • Status in APQP Status Report • Control plan for prototypes
Note on E45: Target date: Prior to production of the parts Only to be used when manufacturing pre-production parts or if the production process needs to be subjected to special monitoring at start-up (containment process)
Note on B46: Production and Inspection of Prototype Parts (APQP Element 10) Aim: To despatch, on schedule, prototypes which meet cost and quality requirements. Expectations: • Dates and quantities for the manufacture of prototypes must be planned, monitored and met • Inspection reports must be supplied with the prototypes (see QSV / S 296002 Part 2 – Production process and product release procedure) • Approval must be obtained from the customer for non-conforming prototypes prior to delivery Documentation with supplier: Prototypes, inspection report Submission to customer: • Status in APQP Status Report • Prototypes and inspection report
Note on E46: Target date: Last date for prototype delivery to ensure that Design Freeze/SOP are not jeoparized.
Note on B47: Design Freeze (Drawings / Specifications) (APQP Element 11) The term "drawings and specifications“ includes all technical drawings, CAD data, material specifications and technical specifications from the customer / supplier. Aim: To provide, on schedule (Design Freeze), all drawings and specifications that are needed to observe the initial volume production sample date/start of production (SOP). Expectations: • The customer must be notified of the latest possible date for making design changes to drawings and specifications to ensure that the planned initial volume production date is met. For product developments this is the deadline for the final volume production drawings • Any "special features“ that have been specified must be given appropriate consideration within the framework of the product and process planning process Documentation with supplier: • Drawings • Specifications Submission to customer: Status in APQP Status Report
Note on E47: Target date: Design Freeze
Note on B48: Confirmation of Manufacturing Feasibility (APQP Element 12) A pan-divisional team must assess the manufacturing feasibility of the intended product within the framework of the contract review. Even if the customer is responsible for the design, the supplier must assess the manufacturing feasibility of the products, both at the quotation/prototype phase and at the planning stage of the volume production process. Aim: To assess production feasibility (volume) relative to the intended design. Expectations: • The team must be convinced that the products is suitable for the intended application and can be produced, checked, packed and delivered to the customer in sufficient quantities, at a competitive price and to the required quality • If subcontractors are involved and their activities have an influence on "special features", the supplier must decide whether to request confirmation of manufacturing feasibility from them Documentation with supplier: Confirmation of manufacturing feasibility Submission to customer: • Status in APQP Status Report • Confirmation of manufacturing feasibility, e.g. to QSV / S 296001 Part 1 - Appendix 4
Note on E48: Target date: In accordance with enquiry text Prior to order allocation
Note on B49: Process Flow Chart and Mass Production Layout (APQP Element 13) The volume production process flow chart is a graphical representation of the planned sequence of operations. Aim: To provide a foundation for investment planning, Process FMEA, production plan, control plan and visual aids. Expectations: To ensure the sequence of all mass production stages and inspection stages from goods inwards through to goods issue Documentation with supplier: • Process flow chart • Machine setting plan Submission to customer: • Status in APQP Status Report • Process flow chart
Note on E49: Target date: Prior to start of Design FMEA Process
Note on B50: Process-FMEA (APQP Element 14) A Process FMEA is a systematic procedure used to ensure that potential production defects and their respective causes have been taken into account and have been countered by preventive measures within a technical pan-divisional team. The Process FMEA, e.g. to VDA 4 or similar, must cover all production and inspection stages and must take into account experiences and concerns. Aim: To prevent defects during process development. Expectations: • All production and inspection stages are listed and analysed • Potential defect modes are described and evaluated and, where necessary, corrective measures are introduced and monitored by the persons responsible • Significant numbers are coordinated with the customer Documentation with supplier: • Process FMEA • Action plan for high risk priority number (RPN) Submission to customer: • Status in APQP Status Report • Cover sheet to Process FMEA including participants and issue level • Pareto analysis of risk priority numbers (top 20 of RPN)
Note on E50: Target date: Final date for initial generation of FMEA Start: With process development, before Design Freeze at the latest End: Completion of outstanding FMEA points for initial sampling
Note on B51: Inspection Equipment Capability (APQP Element 15) Aim: To evaluate the suitability of the intended inspection equipment by means of a measuring system analysis / capability study, e.g. using the MSA method of the AIAG. Expectations: • Capability studies must be carried out in order to check the suitability of the inspection equipment • The customer should be given the opportunity to check the results • Where appropriate, inspection/measurement methods must be agreed in good time with the customer (see APQP element 8.2) • If modifications are made to the inspection and measuring equipment, the capability studies must be repeated Documentation with supplier: Proof of capability with individual values, e.g. printouts from the statistical program used Submission to customer: • Status in APQP Status Report • Proof of capability with individual values within the framework of the production process and product release procedure
Note on E51: Target date: Prior to generating the volume control plan/volume inspection plan (However, the following must be observed: measurement system analyses which relate to existing inspection equipment must be carried out before starting an order for new inspection equipment; for newly purchased inspection equipment, the analysis should be completed when the volume control plan/volume inspection plan is complete
Note on B52: Pre-production Inspection Plan/Pre-launch Inspection Plan (APQP Element 16) Aim: To ensure that process and product requirements are met during pre-production or pre-launch, e.g. through increased inspection frequency, additional inspection features. Expectations: • The type and scope of the inspections and the corresponding inspection equipment for pre-production or pre-launch are defined and agreed with the customer • Reaction plans are defined for handling discrepancies • All "special features“ are included Documentation with supplier: Control plan for pre-production / pre-launch Submission to customer: • Status in APQP Status Report • Control plan for pre-production / pre-launch
Note on E52: Target date: Prior to production of the parts Only applicable if manufacturing pre-production parts or if the volume production process requires special monitoring at start-up (containment process)
Note on B53: Process Instructions (APQP Element 17) All instructions for production personnel, e.g. production plans, work instructions and inspection instructions, maintenance plans, defect catalogues, process parameters. Aim: To ensure quality and quantity Expectations: • Easily understood (available in the national language of the respective production site) and accessible instructions, at the workplace, to ensure that procedures are followed and requirements regarding the process or the product are implemented • Descriptions are given of the procedures involved in controlling defective products • All employees must have been trained or instructed in the tasks they are to perform. Proof of training must be kept and knowledge regulated Documentation with supplier: • Process instructions • Proof of training Submission to customer: Status in APQP Status Report
Note on E53: Target date: Available at workplace for production trial run/initial sampling and employees instructed
Note on B54: Logistics concept (APQP Element 18.1) Aim: To ensure delivery capability in agreement with the relevant customer contact. Expectations: • Call-off system, e.g. Web-EDI • Definition of transport routes • Customs arrangements (where applicable) • Inventory, e.g. consignment warehouse, safety stock Documentation with supplier: Logistics agreement, minimum inventory planning Submission to customer: Status in APQP Status Report
Note on E54: Target date: Before mass production Only applicable when producing pre-series parts or if a control of the mass production at ramp-up is necessary (Containment process).
Note on B55: Packaging Materials (APQP Element 18.2) Aim: To maintain product quality through the use of suitable packaging materials. Expectations: • Suitable packaging materials have been defined for - transport from or to the subcontractor - internal transport/storage - despatch to customer • Packaging specifications and corrosion protection for shipments to the customer have been agreed with the customer • The customer’s packaging specifications must be observed • It must be ensured that the quality of the product is not impaired when it is packed, despatched, put into storage and removed from storage Documentation with supplier: Defined packaging specifications and corrosion protection Submission to customer: • Status in APQP Status Report • Packaging specification agreed with the customer
Note on E55: Target date: Must be available and tested in sufficient quantities by production trial run/initial sample production
Note on B56: Production Trial Run (APQP Element 19) Aim: To check the effectiveness of the mass production process. Expectations: • Use of mass production installations, machinery, tooling, inspection equipment and conditions (including regular operating personnel), also at the subcontractors premises • Use of mass production materials • Verification of the required product quality and the planned nominal quantities (capacity). • Verification of the mass production process • The production quantity must consist of at least one production batch size which is representative of the process (usually daily requirement from annual requirement) • Removal of initial mass production samples • Customer participation, if stipulated beforehand Documentation with supplier: Records and/or proof of capability Submission to customer: Status in APQP Status Report
Note on E56: Target date: Prior to or during initial sampling
Note on B57: Production Inspection/Control Plan (APQP Element 20) Aim: To ensure that process and product requirements are met during volume production. Expectations: • The type and scope of the inspections and the corresponding inspection equipment for volume production are defined and agreed with the customer • Reaction plans are defined for handling discrepancies • All "special features“ are included. Documentation with supplier: Control plan for volume production Submission to customer: • Status in APQP Status Report • Control plan for volume production
Note on E57: Target date: Available at workplace for production trial run/initial sampling process and employees instructed
Note on B58: Preliminary Process Capability Study (APQP Element 21) Process capability studies use statistical methods to prove that the product can be manufactured in line with the specification. Proof of the capabilities of specific features and, where applicable, other features defined with the customer within the framework of APQP must be provided. Aim: To provide statistical proof of capable processes. Expectations: • Provisional process capability under volume production conditions, e.g. to VDA Vol. 4, at Pp/Ppk values of >1,67 (at least 25 x 5 parts) and machine capability (50 parts) at Cm/Cmk values of >1,67 • In the event of incapable processes, suitable corrective measures must be introduced in order to achieve process capability. A 100% inspection must be carried out until process capability is achieved Documentation with supplier: Proof of capability with individual values Submission to customer: • Status in APQP Status Report • Proof of capability with individual values within the framework of the production process and product release procedure • Action plan to achieve required process capabilities, where required
Note on E58: Target date: Prior to intial sampling, on the basis of the parts from the internal production trial run (constituent part of initial sampling process)
Note on B59: Technical Tests on Production Parts (APQP Element 22) Aim: To provide proof that the volumemass product meets customer requirements with the aid of a structured process verification plan (PVP). Expectations: • Technical tests with products from the production trial run, if defined in the design verification plan or in the specification Documentation with supplier: Records and/or examination reports Submission to customer: • Status in APQP Status Report • Proof within the framework of the production process and product release procedure
Note on E59: Target date: Complete by initial sampling
Note on B60: Initial Sampling (PSW) (APQP Element 23) Documented proof that the product manufactured under volume production conditions meets the customer's requirements. The production process and product release procedure is described in detail in Part 2 of QSV / S 296001. Aim: To provide proof of product and process release. Expectations: • To produce, on schedule, the initial volume production samples; to prepare documentation for all elements requested by the customer in accordance with the production process and product release procedure • To provide documentation on schedule; scope in accordance with defined submission level Documentation with supplier: • Initial sample inspection report, initial volume production samples • Documentation for all requested elements in accordance with the production process and product release procedure Submission to customer: • Status in APQP Status Report • Scope in accordance with defined submission level
Note on E60: Target date: Delivery date for initial samples (customer's goods inwards area)

## Action plan
Quality Assurance Agreement with Production Material Suppliers
APQP Status Report - Action plan
Revisions no. | 0 | Date (YYYY-MM-DD) | 0 | Status samples |  | 0
Customer |  | Supplier |  | Customer input
Name | 0 | Name | 0 | Initial sampling date |  | 0
Customer site | 0 | Production site | 0 | PPAP submission level |  | 0
Drawing no. | 0 | Drawing no. | 0 | Project class |  | 0
Revision level | 0 | Revision level | 0
Description | 0 | Description | 0
Date | Element no. | Actions |  | Responsible | Due date (JJJJ-MM-TT) | Status %